## Version History
Project Information
Project:
Client:
Start Date:
Team: | <<Member 1, Member 2, Member 3, ...>>
Date | Description | Version | Author | Reviewer
2016-08-28 | Initial Version | 1 | Janakiram | Sunil
Note:
** Purpose: The purpose of clarification log is to clarify the requirements with the customer, as recorded in the Business Requirements Document (BRD).

## Product Backlog
Product Backlog
User Story ID | Project | Business Process Title | User Stories | Priority | Sprint Details | Owner | Status
USID1 | Study Based application | Customer Interaction | Meeting with the customer | 1 | 1
USID2 | Study Based application | Customer Interaction | Preparation of Clarification Log | 1 | 1
USID3 | Study Based application | Customer Interaction | Creating a Problem Statement | 1 | 1
USID4 | Study Based application | System Definition | Define the System and App Architecture | 1 | 2
USID5 | Study Based application | System Definition | Base Architecture Implementation | 1 | 2
USID6 | Study Based application | System Definition | Infrastructure Requirements Definition | 1 | 2
USID7 | Study Based application | Maintain Users | User Registration | 1 | 3

## Sprint TimeLines
Project Timelines
Sprint No | Title | Start Date | End Date | Duration | Effort - Total | Release Date | Review Date | Success Criteria | Remarks/Comments
1 | Customer Interaction & Requirements Gathering
2 | Application Architecture and System Definition
2 | Base Architecture Implementation & Infrastructure Requirements Definition
3 | Prioritized User Story Implementation
4 | Integration, Testing & Bug Fixing,Release

## Sprint 1 Backlog
Sprint 1 BackLog
Task Id | Project | UserStory ID | User Story | Tasks | Status
T1 | Study Based application | USID1 | Meeting with the customer | Setup the meeting
T2 | Study Based application | USID1 | Meeting with the customer | Invite the necessary stakeholders
T3 | Study Based application | USID1 | Meeting with the customer | Arrange for the required resources for the meeting
T4 | Study Based application | USID2 | Preparation of Clarification Log | Define the clarification log template
T5 | Study Based application | USID2 | Preparation of Clarification Log | Approve the clarification log template
T6 | Study Based application | USID2 | Preparation of Clarification Log | Create clarification log based on the discussion had
T7 | Study Based application | USID2 | Preparation of Clarification Log | Mail to Customer and Product Owner the clarification log
T8 | Study Based application | USID2 | Preparation of Clarification Log | Review and Approve the clarification log
T9 | Study Based application | USID3 | Creating a Problem Statement | Prepare the Problem Statement Template
T10 | Study Based application | USID3 | Creating a Problem Statement | Review and Approve the Problem Statement Template
T11 | Study Based application | USID3 | Creating a Problem Statement | Create the Problem Statement for the application
T12 | Study Based application | USID3 | Creating a Problem Statement | Finalize and approve the Problem Statement

## Sprint 2 Backlog
Sprint 2 BackLog
Task Id | Project | UserStory ID | User Story | Tasks | Status
T1 | Study Based application | USID4 | Define the System and App Architecture | Define the System Architecture
T2 | Study Based application | USID4 | Define the System and App Architecture | Define the Technology Stack
T3 | Study Based application | USID4 | Define the System and App Architecture | Define the Application Architecture
T4 | Study Based application | USID4 | Define the System and App Architecture | Identify the Layers and Components of the application
T5 | Study Based application | USID4 | Define the System and App Architecture | Define the external APIs to be used
T6 | Study Based application | USID4 | Define the System and App Architecture | Identify the Unit Testing Framework to be adopted
T7 | Study Based application | USID5 | Base Architecture Implementation | Create the Project Structure with all Layers
T8 | Study Based application | USID5 | Base Architecture Implementation | Create the Base Data Repository Architecture and Design
T9 | Study Based application | USID5 | Base Architecture Implementation | Create the Models needed for Sprint 1
T10 | Study Based application | USID5 | Base Architecture Implementation | Create Unit Testing Design and Sample Implementation
T11 | Study Based application | USID5 | Base Architecture Implementation | Create sample View and Controller for reference
T12 | Study Based application | USID5 | Base Architecture Implementation | Create the exception classes needed for Sprint 1
T13 | Study Based application | USID6 | Infrastructure Requirements Definition | Create Teams for SVN access
T14 | Study Based application | USID6 | Infrastructure Requirements Definition | Set up SVN for project with team access
T15 | Study Based application | USID6 | Infrastructure Requirements Definition | Set up Build and Release environment for project
T16 | Study Based application | USID6 | Infrastructure Requirements Definition | Communicate to all Stakeholders about the Infra and SVN setup

## Sprint - 3
Sprint BackLog
Task Id | UseStory ID | Project | User Story | Tasks | Resource | Status
T1 | USID7 | Study Based application | User Registration | Create the wireframe for the story |  | closed
T2 | USID7 | Study Based application | User Registration | Create the user story document |  | closed
T3 | USID7 | Study Based application | User Registration | Create the Activity Diagram - flow for user story |  | closed
T4 | USID7 | Study Based application | User Registration | Implement the Data Repository Interfaces, Classes and Models |  | closed
T5 | USID7 | Study Based application | User Registration | Implement the Business Layer |  | closed
T6 | USID7 | Study Based application | User Registration | Write unit tests for the BusinessLayer methods added |  | Open
T7 | USID7 | Study Based application | User Registration | Create the controller for the UI defined |  | closed
T8 | USID7 | Study Based application | User Registration | Write unit tests for controller |  | Open
T9 | USID7 | Study Based application | User Registration | Create the HTML for the wireframe defined |  | closed
T10 | USID7 | Study Based application | User Registration | Integrate the controller and the view |  | closed
T11 | USID7 | Study Based application | User Registration | Write the Functional Test Cases for User Story |  | Open
T12 | USID7 | Study Based application | User Registration | Write the User Acceptance Test Cases for User Story |  | Open
T13 | USID7 | Study Based application | User Registration | Validate Non-Functional Requirements |  | Open
T14 | USID7 | Study Based application | User Registration | Integrate with the application |  | Open
T15 | USID7 | Study Based application | User Registration | CheckIn Code and Unit Tests |  | Open

## Resources IS
Resources Information
SL. No | Name | E - Mail ID | Contact #

## Miscalleneous
Project Repository Details |  |  | Configuration Details
SL. No | Name | Location | SL. No | Name | Location
1 | Code |  | 1 | Study Based application
2 | Documents |  | 2
3 | Design |  | 3
4 |  |  | 4
5 |  |  | 5
Software CheckList |  |  | Hardware Checklist
SL. No | Name | Category | SL. No | Name | Remarks
1 | SQL Server Management Studio | Database | 1
2 | Visual Studio2010 | Software | 2
3 |  |  | 3
4 |  |  | 4
5 |  |  | 5